## Tabelle1
VISION	Become the leading real estate matching website on the market by providing an EQUAL, EASY, EFFICIENT (and AUTONOMOUS) user EXPERIENCE

GOALS	Make landlords/seller as visible as tennants/buyer while giving them control over what information to make public
	Tend more to the needs of the seller (equal to the buyer) than existing plattforms
	Split the bill onto both sides
	Replace the real estate agent thus offering a cheaper service

Project Frame (months)	9			GitHub Subscription	20,00 €
Target Num Employees	4			PyCharm Subscription	20,00 €
				Hardware Setup	2.000,00 €

One time expenses:			Category	Sub Category	Budget	Notes			Milestones	Timeframe (months)
Total	35.000,00 €		Legal	DSVGO	5.000,00 €			1.	Working Demo	0,25
Monthly	3.888,89 €			Website Integrity	10.000,00 €			2.	Full-Feature working Alpha	2,00
						3.	Full UX fleshed out	1,50
			Hardware	PC / Notebooks (TE)	8.000,00 €	Total for all employees		4.	Monetization Strategy in place	0,50
				Mobile Devices (Apple + Android)	2.000,00 €			5.	Web Design done	1,50
						6.	Mobile App done	1,50
			Security	Penetration / User Data Integrity Test	10.000,00 €			7.	Launch marketing strategy	0,25
						8.	Heavy Use Test	0,50
						9.	Stealth Launch	0,25
						10.	Full Launch

						Total	8,25
						Project Frame Buffer (For more Testing)	0,75

Ongoing (monthly)			Category	Sub Category	Budgeted	Notes			Work Packages
Total	30.060,00 €		Marketing	Printing	0,00 €			1.	Core
Total Project Frame	270.540,00 €			Online	0,00 €			2.	Matching Algorithm
				Referral Fees	0,00 €			3.	Database
				Commissions	0,00 €			4.	Data / Cybersecurity
						5.	Front End / UX
			Services	Accounting	1.000,00 €			6.	Mobile App
				Attorney	500,00 €	Possible Legal Advice		7.	Testing
				Contractors	0,00 €			8.	Marketing
				Other	0,00 €			9.	Customer Support
						10.	Business + Accounting
			Travel	Automobile	0,00 €
				Hotels/Lodging	0,00 €
				Other	200,00 €

			Technology / Licensing	GitHub Company (TE)	80,00 €	Total for all employees			TechStack
				PyCharm (TE)	80,00 €	Total for all employees			FrontEnd
				Hosting	200,00 €				Bootstrap5
				Other	2.000,00 €	Unknown Unknowns			JavaScript
						HTML 5 / CSS
			Personnel	Back End / Database Engineer	7.000,00 €
				Front End / UX Engineer	7.000,00 €				Software
				Testing / Cyber Security Engineer	7.000,00 €				GitHub
				Core / Mobile Plattform Developer	3.000,00 €				PyCharm
				Risk Buffer	2.000,00 €	Re-Hire / Drop-Out / Sickness
						BackEnd
						MySql
						Django
End Total	305.540,00 €					PythonAnywhere
						Python